Notes from the meeting of the Neighbourhood Planning Working Group held on 31 August 2016 at 7.00pm.

Present:- Cllr Terry Cryer, Cllr Mrs Lynda Cryer, Councillor David Hindle, Councillor Mrs Lindsay Philipson, Councillor Mrs Eileen Murray, David Willis, City Councillor Neil Cartwright and Sue Whittam.

Lindsay welcomed everyone to the meeting and after introductions it was noted that Tim Brown, Tony Ingham and Councillor Keith Middlebrough had given their apologies for this evening’s meeting.

There was a quick update on progress made so far – the proposed area of designation had been submitted to Preston City Council (PCC) for approval and was currently out for consultation on both the PCC and the Parish Council’s website.  It was noted that the closing date for comments was 2 September 2016.  A report would then be submitted to PCC’s Cabinet on 28 September 2016 when hopefully approval would be given to the area of designation for the Grimsargh Neighbourhood Plan.  Sue also reported that Gladman Developments had responded to PCC about our area of designation application and this would be dealt with by PCC.

To help with background to the project a copy of the notes from the Neighbourhood Planning Working Group held on 27 July 2016 was circulated together with a copy of Broughton’s Questionnaire.

Lindsay explained that a meeting had been arranged with Community Futures to discuss how they could help and support our Neighbourhood Plan – Sue and Lindsay would be attending this meeting on Wednesday 7 September 2016.

Terry confirmed he had contacted Amelia at AVJ regarding the production of maps, fliers and questionnaires and as a ball park figure Amelia had quoted at around £50 per hour but she would be able to give a firm estimate once we knew what work needed to be done.

Next Steps

Lindsay explained that this meeting had been arranged to brainstorm the ideas for taking the project forward and, in particular to look at the suggested theme groups to see if the group felt that this was the right approach and that all the main issues had been included.  We were currently at the very early stages of developing our Neighbourhood Plan and the Working Group had now been extended into the Steering Group which would guide and take the project forward.

The Group then looked at all the themes in detail and agreed the following:-

- Housing including extra care housing – Eileen to see if Tony Ingham would wish to be involved in this group.  Note that there are good examples of extra care housing at Salford and also Longton.

- Ecology and Heritage – David H happy to be involved and take this group forward.

- Community & Social including children/young people – Sue to ask Keith M if he wished to take this group forward.

- Health, wellbeing and fitness including you facilities (MUGA) – David W confirmed he was happy to be involved and take this group forward.

- Environment, Infrastructure (to include utilities – water, gas, electric, phones and sewage), built & green spaces including sustainability – Eileen M to take this group forward.

- Access, Infrastructure (to include transport links/pedestrian flows/traffic) and Accessibility + cycling and footpaths – lead person to be decided.

- Business and Employment – David W to contact Damien Perkins to see if he wishes to be involved.

- Safety and Security – including crime prevention, road safety and pavements – this will obviously involve the police but a lead person is needed for this group.

David W commented that the themes seemed to be the right ones and he felt very comfortable with progress so far.  Neil suggested that Liz Mossop from PCC may be able to help with community engagement.  However Lindsay suggested that we wait now until after the meeting with Community Futures, then we could identify what support would be given and plan for any omissions.  It was felt that we should tailor the questionnaire to follow our suggested themes.

Eileen had started some work on the timeline and would meet with Sue when she returned from her holidays.  Eileen would also set up a separate dropbox account so all the group could access the Neighbourhood Planning documents.

Date of next meeting

It was agreed that the next meeting would be held on 5 October at 7.00pm in the village hall.  Lindsay said that we would schedule the meetings to last around 1.5 hours.